## Sheet1
APPROVED by the order of the director of the branch “Nazarbayev Intellectual School of Chemical and Biological Directions in Shymkent” JSC “Nazarbayev Intellectual Schools” ______________Kasimov B.M. dated August 29, 2023 235 OD
DEVELOPMENT PLAN, “Changing the world, start with yourself” Nazarbayev Intellectual School of Chemical and Biological Directions in Shymkent for calendar years 2021-2025
No. | Action/event | Connection with the development strategy of AOO until 2030 | Responsible for implementation | Resources | Monitoring/deadlines-intermediate and final (who/how/when?) | Expected Result
Section 1. Brief analysis of the current state of development of the Intellectual School
General information:
Nazarbayev Intellectual School of Chemical and Biological Directions in Shymkent (hereinafter referred to as the Intellectual School) began its activities on February 25, 2013. The school building is designed for 720 students from secondary schools in the region and the country who passed a competitive selection. As of August 2023, 805 students are studying from grades 7 to 12. The school is designed to ensure high-quality growth in education, the introduction of innovative approaches and teaching methods into the educational process, and continuous professional development of teaching staff. The Intellectual School has been a member of the UNESCO Associated Schools since November 19, 2015, and has had the official status of an accredited school of the Council of International Schools since December 2017. In 2023, the preliminary stage of the re-accreditation period passed. Teaching staff undergo certification on a regular basis in order to improve their professional level: in September 2023, 1 researcher, 42 expert teachers, 57 teacher-moderators, 21 teachers and 1 trainee teacher are working at the school. A cluster of certified trainers of Kazakhstan and international levels has been created, which makes up 47% of the total number of teachers. According to the level of education, the school employs: 27 teachers with a specialist diploma, 41 teachers with a bachelor’s degree, 60 teachers with a master’s degree. There are 15% more master's students than the planned value of the school development plan and the indicators of Strategy 2030. 2 candidates of biological sciences and 1 phD have a scientific degree. Also in 2022, the number of teachers enrolled in master's and Ph.D. programs increased. There are 4 teachers studying for PhD candidates, 12 teachers for future master's students. The school has a career guidance inspector who helps students and graduates decide on their future profession, choose the right subjects of study, and apply to universities. Also, the career guidance consultant organizes meetings with local and foreign universities to determine the choice of specialties and universities for school graduates, conducts consultations throughout the year on obtaining grants for graduates, and provides documentary support for students when submitting documents to universities. From 2015 to 2023, the school graduated 8 batches of graduates. A total of 871 graduates graduated from the school. Of these, 302 are studying at NU, 107 graduates are studying at foreign universities in 16 countries. In 2023, out of 81 students, 40 students (which is 49%)entered Nazarbayev University and were awarded a letter of gratitude by the senior management of Nazarbayev University. Students show high results in the following areas: Olympiad movement, scientific project competition, startups and Robotics championships. Every year, in the Republican Olympiad in general education subjects among students in grades 9-11 (12), the Intellectual School shows high results and is in the ranking of the 100 best schools in Kazakhstan. 2021 – 21st place, 2022 – 17th place, 2023 – 23rd place. Students participating in international olympiads in the subject of geography EGeo (2021, 2022, 2023), IGeO (2021, 2022, 2023), IESO (2022, 2023) became silver and bronze medalists. At the International Competition IGEM (synthetic biology), held annually in Paris (France), the school team won a bronze medal in 2022, and a gold medal in 2023. At the International Roboland Championship (3rd place, 2022), FIRST in the USA (3rd place 2023), the school team in Robotics, students showed their key skills necessary for robotics, and were identified in the category "Best Innovative Project" To date, Intellectual School has 3 foreign partner schools. 1.Lucky International School, India; 2. Städtische Realschule, Germany, Berlin; 3.Suzhou Industrial Park Foreign Language school, China
Strengths
International accreditation CIS 2017, positive feedback from the preliminary assessment of the CIS accreditation group
100% admission to universities, increasing the share of graduates entering foreign universities and Nazarbayev University
Prize-winners of the International Olympiad in the subject of Geography and Robotics
In terms of stability of VSE results, the school is at the level of high stability, high result
Weak sides
Lack of teaching experience in 2-3 languages
Low rates of prizes in scientific project competitions in science and mathematics
Low research and journalistic activity among school staff
Risks
Leakage of specialists teaching in 3 languages ​​due to the unattractiveness of the current social package and remuneration
Possibilities
Organization of in-school courses for teachers
Launching activities and projects to develop research skills, functional literacy and educational projects
School greenhouse and other research sites for the development of research activities
Cooperation between partner schools and joint projects
Creation of highly effective school communities for the implementation of the “Unity in Diversity” project
Section 2 |  | Basic provisions about the school (mission, leadership, values)
Mission |  | We learn and build a better world by opening our hearts and minds.
Vision |  | Motto: Change begins with yourself - We are a team of close-knit, high-class teachers who strive to be recognized leaders in education, helping students to be citizens of the world and achieve success in a rapidly developing information space.
Values |  | Respect • Transparency • Patriotism and Responsibility • Hard Work and Creativity • Honesty • Family Values ​​and Traditions • Health and Wellness • Global Citizenship
Section 3 Sustainable development of Intellectual schools |  | Teaching, learning and assessment
Priority 1 Improving educational and methodological support for the process of implementing the educational program, teaching materials; Consider the possibility of introducing into the curriculum elective courses / club activities / extracurricular activities for the development and implementation of school values, the values ​​of “Mangilik El”, the “Rukhani Zhangyru” program, service to society |  | Indicator 1 (Indicator-26 from the Strategy) Quality of knowledge at the end of the academic year 2021 - 87% 2022 - 88% 2023 -90% 2024 - 91% 2025 - 93% Indicator 2 (Indicator-11 from the Strategy) Proportion of students organizing nationwide events of the “Rukhani Zhangyru” program 2021 – 15% 2022 – 15% 2023 – 15% 2024 – 20% 2025 – 20% Indicator 3 (Indicator-12 from the Strategy) The share of students involved in social projects, practices, promotions and additional education 2021 – 90% 2022 – 90% 2023 – 90% 2024 – 90% 2025 – 90%
1 | Determining the individual needs of students to improve the teaching process and the form of personalized learning | R-3, SN-1, P - 6 | ShKPO commission, teachers, psychologists, curators | Responsible executors | Every quarter | General and individual report on students every quarter. Minutes of meetings.
2 | Monitoring the effectiveness of educational program implementation | H-3. SN-1, P-5 | Deputy Directors | Training program. Heads of the Moscow Region, coordinators of the educational program. | Once a school year annually, annual analysis. | Development of recommendations for updating subject programs.
3 | Using the results of monitoring educational achievements of students to improve the quality of education | R-3, SN-1, P-26 | Deputy Directors | Analytical reports of the Research Center, minutes of meetings of the Moscow Region. Deputy director of the SD, methodologist, heads of the Moscow Region, students of grades 7-12, teachers. | Discussion at meetings of methodological associations once every six months. | Teachers draw up a plan for individual work to eliminate gaps in students’ knowledge and build an individual development trajectory.
4 | Conducting integrated lessons and assessing student achievements | R-3, SN-1, P - 26 | Heads of the Ministry of Defense, Deputy Directors for Research and Development and SD | Methodist, Teachers, Lesson schedule, Interdisciplinary communication table, classrooms | According to the schedule annually Observing lessons, conducting surveys and interviews with students | Schedule of integrated lessons; Analytical report on the effectiveness of integrated lessons
5 | Reflexive pool based on the results of external and internal assessment | R-3, SN-1, P - 26 | Deputy Directors | Analytical reports of the Research Center, minutes of meetings of the Moscow Region. Deputy directors, heads of the Moscow Region, teachers, students in grades 10 and 12. | Analysis of the results of SOCH and VSO - 1 time per quarter; CO analysis - once a year. | Developing teacher reflective skills to improve professional performance using tools for analyzing student learning outcomes.
6 | Organization of events that develop global competencies and global citizenship, feelings of patriotism of students during class and extracurricular activities | R-3, SN-1, P-11 | Deputy Directors for HR and SD, Heads of the Moscow Region, teacher-organizer-curator, educators, librarian | Teachers, curators, project coordinators | Conferences Model UN, flash mobs of dombra players, dance competitions for the Day of Tolerance. According to the event plan and the annual plan of the BP, schools are held according to the schedule - November-December | Event plans
7 | Development of the Moodle platform for personalized learning for students | R-3, SN-1, P-6 | Deputy Director for SD, methodologist, Heads of the Moscow Region | Subject teachers, computer science teachers, IT personnel, curators | The Deputy Director for SD does monitoring every quarter, adding to the database throughout the year | Moodle website, user monitoring
Priority 2 Implementation of effective procedures by the school to prepare students for admission to leading foreign and Kazakh universities |  | Indicator 4 (Indicator-27 from the Strategy) Dynamics of successful admission of school graduates to prestigious higher educational institutions in Kazakhstan and foreign countries 2021 - 98% 2022 - 98% 2023 - 98% 2024 - 98% 2025 - 98% Indicator 5 ( Indicator-27 from the Strategy) Dynamics of successful admission of school graduates to Nazarbayev University 2021 - 35% 2022 - 35% 2023 - 37% 2024 - 37% 2025 - 40% Indicator 6 (Indicator-27 from the Strategy) Average level of results IELTS 2021 – 6.5 2022 – 6.6 2023 – 6.7 2024 – 6.7 2025 – 6.8
1 | Drawing up individual development plans for each high school student (filled out in the eios program) | R-3, SN-1, P - 27 | Career guidance, Deputy Director for SD and HR | Heads of the Moscow Region, teachers, psychologists, curators, parents | During the year, the Deputy Director for SD monitors | Individual student development plan Performance report Completed eios database
2 | Organization of international exams on the basis of the school for admission to foreign universities | R-3, SN-1, P - 27 | Deputy Director for SD, career guidance specialist, | School technical staff, school equipment | According to the schedule annually Deputy Director for SD materials, results | Report, exam results
3 | Drawing up a schedule for preparing additional lessons and elective courses for exams for admission to Kazakh and foreign universities | R-3, SN-1, P - 27 | Deputy Director for SD, methodologist, heads of the Moscow Region | Teachers, methodologist, career guidance, course programs | September, January annually Deputy Director for SD materials, results | Schedule and schedule of additional lessons
Priority 3 Support with resources and materials for the teaching and learning process |  | Indicator 7 (Indicator-7 from the Strategy) Teaching materials, collections of tasks for each subject and teaching aids have been created 2021 - 5 2022 - 6 2023 - 7 2024 - 8 2025 - 9
1 | Development of teaching materials and collections of problems, teaching aids for teachers on parallels, sections, topics and types of exams | R-3, SN-1, P-7 | Program coordinators, heads of educational organizations, teachers, curators Deputy Director for SD and scientific development | Teachers, curators | June annually Deputy Director for SD and NMR materials, results | Methodological developments
2 | Organization of integrated work of educational psychologists with the teaching staff of the school to determine approaches to teaching students and the use of differentiation in the educational process | R-3, CH-1 | Expert teachers, trainers, educational psychologists | Teachers, learning style test results, materials | Annually according to schedule Deputy Director for SD materials, results | Minutes of MO meetings Report on the results of joint work of school educational psychologists with teaching staff
3 | Ensuring the educational process and self-education through library, bibliographic and information services for students, parents and the teaching staff of the school | R-3, CH-1 | Teacher-librarians | Teacher-librarians, familiarization with library resources, bibliographic references | According to the work plan | Satisfying the information needs of users
4 | Constant study of the information needs of teachers and students in order to effectively develop library resources | R-3, CH-1 | Teacher-librarians | Teacher-librarians, conversation, survey, book requests | According to the work plan | Fund corresponding to NIS-Programme and user requests
Priority 4 Development of the Olympiad movement and research activities of students |  | Indicator 8 (Indicator-24 from the Strategy) Share of winners of Republican and International Olympiads and scientific competitions of schoolchildren from the total number of student participants of Intellectual Schools 2021 - 50% 2022 - 50% 2023 - 50% 2024 - 50% 2025 - 50% Indicator 9 (Indicator-49 from the Strategy) Proportion of students performing at republican and international competitions and conferences 2021 – 1% 2022 – 1% 2023 – 1% 2024 – 2% 2025 – 2% Indicator 2 of Strategies Number of intellectual products that have received recognition in the country and abroad 2021 - 1 2022 - 2 2023 - 3 2024 - 4 2025 - 5 Indicator 3 from the Strategy Number of scientific and research projects of students that have received recognition in the country and abroad 2021 – 1 2022 – 2 2023 – 3 2024 – 4 2025 – 5
1 | Implementation of the “Olympic Hope” project | R-3, SN-1, P-24 | Deputy Director for Research and Development | Teachers preparing for the Olympiads, attracted specialists, Olympic reserve. Methodological developments and manuals for preparing for the Olympiads. | Every year in September - the formation of lists and approval of the work plan. In each quarter there are rating Olympiads. | Students show results at national and international Olympiads.
2 | Developing student research skills | R-3, SN-1, P-24, P-49, I-2, I-3 | Deputy Director for Research and Development | Formation of lists and approval of the work plan. Digest for students on competitions, conferences and competitions. | Every year during the year, according to the digest, students participate in competitions and conferences at various levels. | Students develop research skills and show the results of projects at national and international competitions and conferences.
3 | Implementation of the "STEAM Lab" project | R-3, SN-1, P-24, P-49, I-2, I-3 | Deputy Director for Research and Development | Formation of lists and approval of the work plan. Digest for students on competitions, conferences and competitions. | Every year during the year, students participate in competitions and conferences at various levels. | Students develop research skills and show the results of projects at national and international competitions and conferences.
4 | Preparation of scientific project products for obtaining copyright certificates and patents | R-3, I-2, I-3 | Deputy Director for Research and Development | Teachers, students, parents, scientists from universities | Every year throughout the year, teachers and students are engaged in research projects. Filing applications for copyright certificates and patents | Students develop research skills and show the results of projects at national and international competitions and conferences.
| Priority 5. Preparation for the next stage of international accreditation (confirmation of the status of an accredited school) | Indicator 5 from the Strategy Indicator 10: Confirmation of the status of an accredited school: 2021 - preparation for the self-assessment process 2022 - preparation for the preparatory assessment 2023 - preparation for the team assessment 2024 - school accredited, FRPP report 2025 - preparation for the self-assessment process
1 | FRPP Report on Team Visit Recommendations | I-5 | Deputy Directors for Research and Development | Deputy directors, plans, events, reports | August-September 2020 | Report
2 | Implementation of the self-assessment process according to CIS standards and indicators | I-5 | Deputy Directors for Research and Development | Deputy directors, plans, events, reports | September-December 2021 | Self-assessment report
3 | Preparing for a team visit | I-5 | Deputy Directors for Research and Development | Deputy directors, plans, events, reports | September-December 2022 | Report
Section 4 |  | Management and Leadership
Priority 1 Support and coordination of innovative approaches to school management |  | Indicator 11 (Indicator 1 from the Strategy) The School Board of Trustees is functioning 2021-2025. The composition of the PS is approved annually Indicator 12 (Indicator 4 from the Strategy) Annual report on the activities of Intellectual Schools 2021-2025. A report is provided annually. Indicator 13 (Indicator 14 from the Strategy) Functioning of the network association of school graduates: 2021-2025. functioning
1 | Implementation of activities: -Pedagogical Council -Methodological Council -Board of Trustees -Council for Translating Experience -School Certification Commission -Parent Committee -Student Council | R-2, SN-1, P-1, P-4 | Director | Members of management bodies | 2021-2025 Annually according to schedule Administration Photo and video archive | Determination and further development of school priority areas with the help of advisory bodies and creative groups. Work plans, minutes of meetings, annual performance reports.
2 | Conducting sharing meetings with representatives of the Moscow Region, the parent committee, the Board of Trustees on school development issues | R-2, SN-1, P-1 | Director | Director, teachers, Board of Trustees, parent committee | 2021-2025 according to schedule | As a result of these meetings, a school-wide vision of school development will be formed.
3 | Drawing up, coordination and approval of the School PS Annual Work Plan | R-2, SN-1, P-1 | Director | PS members | 2021-2025 December-January | PS work plan
4 | Analysis of school PS activities | R-2, CH -1, P-1 | Director | PS Secretary, Director | 2021-2025 December | Analytical report for the year
5 | Execution of protocol decisions following meetings of the Board of Directors | R-2, CH -1, P-4 | Director | Miscellaneous as needed and questions asked | As needed | Executed protocol solutions.
6 | Monitoring PRISH | R-3, SN-1, P-4 | Director | Deputy Directors | 2021-2025 Quarterly until the 5th day of the month following the quarter | Analysis and amendments to the PRIS, if necessary, analytical reports based on monitoring results.
7 | Development of an annual report on school activities | R-3, SN-1, P-4 | Deputy Directors | Responsible executors | 2021-2025 December – January annually | Developed annual report on school activities
8 | Monitoring the strengths and weaknesses of the school. Development of a School Development Plan for 2026-2030 (calendar) years | R-3, CH -1, P-1 | Deputy Directors | Questionnaire results, Student Voices, analysis of the strengths and weaknesses of the school’s activities, results of the quality of students’ knowledge for the year, results of the VSE, analysis of the MO, results of monitoring of the current PRIS, Development Strategy of the AEO until 2030. | 2025 3rd-4th quarter | Agreed and approved PRISH for 2021-2025 (calendar) years
9 | Participation in the annual alumni forum with the involvement of the Board of Trustees | R-3, SN-3, P-14, P-17 | Deputy Director for HR, career guidance consultant | School graduates, Teachers, City business community. | Once every two years | Creation of a platform for graduates and potential employers on the basis of the school
Priority 2 Ensure continuity of leadership and effective support in the current and long-term activities of the school. |  | Indicator 14 Level of targeted training of the personnel reserve 2021 - 100% 2022 - 100% 2023 - 100% 2024 - 100% 2025 - 100% Indicator 15 (Indicator 34 from the Strategy) Functioning of the network community of teacher leaders of Intellectual schools, generating ideas worthy of dissemination 2020 – functioning Indicator 16 (Indicator 10 from the Strategy) Functioning of a network community of student leaders of Intellectual schools generating ideas worthy of dissemination 2020 – functioning
1 | Formation of a personnel reserve for filling management positions in the structural divisions of the AUP | R-3, CH-1 | Deputy Director for Development, HR Inspector | Heads of Moscow Region, teachers | The list is approved annually by the director of the branch | List of employees for management positions in the structural divisions of the AUP
2 | Involving student members of the self-government body in the development of school leadership communities | R-3, SN-1, P-34 | Deputy Director for Educational Work, coordinator of the "School Self-Government" project, curators | curators, students | annually in September - approval of work plans | school government work plan
3 | Implementation of the activities of the network community of student leaders of Intellectual Schools, generating ideas worthy of dissemination | R-3, SN-1, P-10 | Deputy Director for Educational Work, coordinator of the "NIS Talks" project, curators | teachers, curators, work plans, performance scripts | Annually in September - approval of work plans, quarterly monitoring of meetings, speeches, conferences at the city level | work plans, activity report, ideas, skills
4 | Functioning of a network community of teacher leaders of Intellectual Schools generating ideas worthy of dissemination | R-3, SN-1, P-34 | Deputy Directors | Deputy directors, teaching staff | Every year in September – formation of groups, approval of the list of participants. Annually – monitoring through presentations. | Functioning of a network community of teacher leaders of Intellectual Schools generating ideas worthy of dissemination
Priority 3 Support the process of studying regulations by school staff |  | Indicator 17 Level of assimilation by newly admitted members of the school community of the content of regulatory, instructive and methodological documents 2021 - 100% 2022 - 100% 2023 - 100% 2024 - 100% 2025 - 100% Indicator 18 Level of assimilation by newly admitted members school community procedures for applying for services and receiving funds 2021 - 100% 2022 - 100% 2023 - 100% 2024 - 100% 2025 - 100%
1 | Conducting explanatory work on regulatory documents for the school community and ensuring their further application in practice | R-3, CH-1 | Lawyer; Personnel Inspector; Safety and Health Engineer | Heads of the Ministry of Education, Curators Teachers, Regulatory documents; | August-September annually August-September annually Deputy Directors for SD and HR Attending events to clarify regulatory documents | Orientation days program
2 | Conducting explanatory work on instructional and methodological documents for teaching staff and students | R-3, CH-1 | Lawyer, Heads of Moscow Region | Teachers, instructional and methodological documents; | August-September annually Deputy Directors for SD and HR Attendance at outreach events | Orientation days program
3 | Conducting explanatory work for newly hired teachers on the procedure for submitting an application for the necessary educational materials and equipment, timely allocation of funds to the budget | R-3, CH-1 | Deputy Director for FCD | Economists, application form for training materials and technical equipment | August-January annually Deputy Directors for SD and HR | Orientation days program
Section 5 |  | Staff
Priority 1 Improving the qualifications of school teachers and conducting certification of teaching staff and persons equivalent to them |  | Indicator 19 (Indicator 28 from the Strategy) Share of teachers with a level of pedagogical excellence (%) 2021 - “trainee teacher” - 8%, “teacher” - 24%, “teacher-moderator” - 51%, “expert teacher” " - 16%, "teacher-researcher" - 0%, "teacher-master" - 0%. 2022 - “trainee teacher” - 7%, “teacher” - 23%, “teacher-moderator” - 52%, “expert teacher” - 17%, “teacher-researcher” - 0.3%, “teacher – master” - 0%. 2023 - “trainee teacher” - 6%, “teacher” - 22%, “teacher-moderator” - 53%, “expert teacher” - 18%, “teacher-researcher” - 0.4%, “teacher – master” - 0%. 2024 - “trainee teacher” - 5%, “teacher” - 21%, “teacher-moderator” - 54%, “expert teacher” - 19%, “teacher-researcher” - 0.5%, “teacher – master” - 0%. 2025 - “trainee teacher” - 4%, “teacher” - 20%, “teacher-moderator” - 55%, “expert teacher” - 20%, “teacher-researcher” - 0.6%, “teacher – master” - 0%. Indicator 20 (Indicator 30 from the Strategy) Share of foreign teachers in Intellectual schools from the total number of teachers 2021 - 5% 2022 - 5% 2023 - 5% 2024 - 5% 2025 - 5% Indicator 21 (Indicator 31 from the Strategy ) Number of certified teacher-trainers from the total number of teachers 2021 - 40 2022 - 41 2023 - 42 2024 - 43 2025 - 44 Indicator 22 (Indicator 32 from the Strategy) The share of employees with an academic master's degree 2021 - 27% 2022 - 29%; 2023 -31%; 2024 - 33%; 2025 - 35%.
1 | Increasing the level of skill of teaching staff (approval of the preparation plan for certification of teaching staff and equivalent persons) | R-3, SN-1, P-28 | Deputy Director for Development, heads of the Ministry of Defense, professional development trainers, HR inspector | List of workers subject to certification | Every year in September – formation of a list of those certified, approval of the working group for preparation for certification, work plan, lesson schedule. According to the schedule - observing lessons, writing reports. | Order for certification, approved lists. In June there is a meeting of the AC. Teaching staff successfully pass annual school assessments as part of certification.
2 | Creation of a cluster of certified trainers of Kazakhstan and international level | R-3, SN-1, P-31 | Deputy Directors, HR Inspector | Advanced training courses in the country and abroad | Annually - according to the schedule of courses of JSC "Nazarbayev Intellectual Schools" | The internal potential of certified trainers will contribute to the growth of professional development of school teachers
3 | Creating conditions for the professional growth of teaching staff through obtaining an academic degree (master's and doctoral studies) | R-3, SN-1, P-32 | School Director, Deputy Directors | Teachers, Internet resources | Annually – interviews with candidates, constant support of the teacher. Providing study leaves with retention of position. | A comprehensive system of professional development for teachers has been created in accordance with international standards
4 | Organization of advanced training courses within the school | R-3, SN-1, P-31 | Deputy directors, heads of the Moscow Region | Certified trainers, teacher coaches | Every year in September – approval of the list of necessary directions for PCs, participants and trainers. Once a month – monitoring the quality of courses and attendance. In March – presentation of PC course results. | A comprehensive system of professional development for teachers has been created in accordance with international standards. Teachers and teaching staff constantly improve their qualifications.
5 | Organization of work for foreign teachers | R-3, SN-1, P-30 | School Director, Deputy Directors | Foreign teachers | Annually in the 1st quarter of the actual year | Concluding agreements with foreign teachers
Priority 2 Supporting the professional development of teachers and other teaching staff; Development of language competencies of teaching staff. Research activities of teachers and equivalent persons (conducting lesson research, practice research, publications and participation in conferences) |  | Indicator 23 (Indicator 29 from the Strategy) Share of teaching staff and equivalent persons of Intellectual schools who speak Kazakh, Russian and foreign languages ​​2021 - 25% 2022 - 26% 2023 - 27% 2024 - 28% 2025 - 30 % Indicator 24 (indicator 34 from strategy) The functioning of the network community of leaders -teachers of intellectual schools generating ideas worthy of the distribution of 2021 - 2022 is functioning - 2023 is functioning - 2025 operates - the indicator 25 (indicator 46 from the strategy. ) Number of publications in scientific publications with a non-zero impact factor 2021 - 1 2022 - 1 2023 - 2 2024 - 2 2025 - 2 Indicator 26 (Indicator 47 from the Strategy) Proportion of teachers speaking at republican and international competitions and conferences , of the total number of teachers of Intellectual schools 2021 - 0.5% 2022 - 1% 2023 - 1.5% 2024 - 2% 2025 - 2.5% Indicator 27 (Indicator 35 from the Strategy) Number of teachers trained development of teaching materials 2021 - 35 2022 - 37 2023 - 40 2024 - 42 2025 - 45 Indicator 28 (Indicator 36 from the Strategy) Number of teachers trained in the development of assessment tools and procedures 2021 - 20 2022 - 22 2023 - 24 2024 - 26 2025 - 28
1 | Training of teachers on the development of teaching materials and assessment tools | R-3, SN-1, P-35, 36 | Deputy Directors | Deputy directors, teaching staff | Every year during the year according to the schedule of the Center for Public Policy, Center for Pilots | Trained teaching staff to develop teaching materials and assessment tools
2 | Development of research skills of teaching staff through “Action Research” and “Lesson Study” | R-3, SN-1, P-46, 47 | Deputy Directors | Deputy directors, teaching staff | Every year in September – formation of groups, approval of the list of participants. Annually – monitoring through presentations. | Teaching staff participate in republican and international competitions, conferences and publish research results in scientific publications with a non-zero impact factor.
3 | Experts Lab laboratory of expert teachers | R-3, SN-1, P-46, 47 | Deputy Directors | expert teachers | Expert teachers share their best practices with colleagues. Every year in September - organization of the “Experts Lab” work, approval of plans and lists of participants. Throughout the year - presentation of work results at forums and conferences | Teaching staff participate in republican and international competitions, conferences and publish research results in scientific publications with a non-zero impact factor.
4 | Improving the English language proficiency of teachers teaching in high school in English | R-3, SN-1, P-29 | Deputy Directors | English teachers, CLIL and IELTS preparation trainers, librarians | Every year in September – approval of the list of teachers and trainers. Monthly – monitoring the quality of delivery and attendance of courses. Annually – monitoring through the IELTS exam. | Teaching in English is carried out by a large number of Kazakhstani teachers
5 | Improving the level of Kazakh language proficiency of teaching staff | R-3, SN-1, P-29 | Deputy Directors | Kazakh language teachers, librarians | Every year in September – formation of groups, approval of the list of participants and trainers. Monthly – monitoring the quality of delivery and attendance of courses. Annually - monitoring through the KAZTEST exam. | The quality of teaching in the academic Kazakh language and the quality of knowledge in subjects are improving
6 | Improving the level of proficiency in three languages ​​of teaching staff | R-3, SN-1, P-29 | Deputy Directors | Language courses, CLIL strategies, Internet resources. | Annual language exams. Every six months the database is updated. | Development of a system of trilingual educational space at school
Section 6 |  | Availability of education
Priority 1 Ensure a safe and supportive environment for teaching and learning |  | Indicator 29 (Indicator 12 from the Strategy) Percentage of students in grades 1-12 of Intellectual schools involved in social projects, practices, actions and additional education 2021 – 90% 2022 – 90% 2023 – 90% 2024 – 90% 2025 – 90%
1 | In order to successfully complete the process of confirming the status of an accredited school, continue to work on organizing safe conditions and life activities. | R-3, CH-1 (System of educational work) | Deputy Directors | Heads of educational institutions, teacher-organizers-curators, teachers, students, technical staff. | Constantly, August-September annually | Ensuring the health and life safety of those in the school building
2 | Conducting induction training for all new students and newly hired teachers, as well as school technical staff. | R-3, CH-1 (System of educational work) | HSE engineer | Newly hired staff and student | Constantly, August-September annually | Compliance with safety measures and prevention of various injuries in the workplace
3 | In order to ensure the safety of students and school staff when crossing the road into the territory and streets located opposite the school, organize daily duty of school staff and police officers of the Karatau District Department of Internal Affairs. | R-3, CH-1 (System of educational work) | HSE engineer | Heads of educational institutions, teacher-organizers-curators, teachers, students, technical staff | Daily according to the director’s order and schedule Supervising Deputy Director | Ensuring safety and compliance with traffic rules when crossing the road
8 | Implementation of the project “Serving Society” | R-3, SN-1, P-12 | Deputy Director for VR | Curators, teachers | Deputy directors of BP supervise the work of the project, work is carried out throughout the year according to the approved work plan | Event plans, social projects
5 | Organization of Russian language courses for hostel students (Rural children) | R-3, CH-1 (System of educational work) | Educators, Russian language teachers | Educators, Russian language teachers | the work plan is approved in September, work is carried out throughout each academic year | Mastering spoken and academic Russian language
6 | Increasing the number of sports clubs to create teams of different age groups in football for boys and volleyball for girls | R-3, CH-1 (System of educational work) | Educators, physical education teachers | Educators, physical education teachers | in September of each academic year, a work plan for the hostel’s circle activities is approved | Effective participation of dormitory students in sports competitions on a city, regional and republican scale
7 | Organization of ICT courses for educators for use in group work (Corel Draw, Photoshop, 3D Max and other computer programs) | R-3, CH-1 (System of educational work) | Educators, art and computer science teachers | Educators, art and computer science teachers | in September of each academic year, a work plan for in-school courses among teachers is approved. school employees | Mastering new skills and organizing new clubs in the hostel
8 | Organize a dombra orchestra from among the students of the hostel | R-3, CH-1 (System of educational work) | Educators, additional education teachers | Educators, additional education teachers | in September of each academic year, a work plan for the hostel’s circle activities is approved | Participation in creative competitions on a city, regional and national scale, performance in school events
9 | Strong family program for parents and children | R-3, CH-1 (System of educational work) | Psychological service | curators | 2021-2022 academic year | Parents and children acquire effective communication skills, improving parent-child relationships
10 | Organization of school events dedicated to international days according to the UN calendar with the involvement of parents | R-3, CH-1 (System of educational work) | Psychological service | Psychologists, curators, educators, parents | in September of each academic year, a plan is approved to instill global citizenship competencies in accordance with the international days of the UN calendar
11 | Organization of interest clubs “Psychology for teenagers” among student volunteers | R-3, CH-1 (System of educational work) | Psychological service | Psychologists, curators, educators, | approval of the club’s work plan, organization of club meetings once a month | Volunteers develop leadership skills and help prevent self-destructive behavior among teenagers
12 | Organize a dance group from among the students of the hostel | R-3, CH-1 (System of educational work) | Educators, additional education teachers | Educators, additional education teachers | in September of each academic year, a work plan for the hostel’s circle activities is approved | Participation in creative competitions on a city, regional and national scale, performance in school events
Priority 2 Improving access to education for students |  | Indicator 30 Level of satisfaction of teachers and students with the quality of support provided 2021 –100% 2022 –100% 2023 –100% 2024 – 100% 2025 – 100%
1 | Development of elective course programs in a 2nd foreign language | R-3, CH-1, | Deputy Director for SD, methodologist | Teachers of 2nd foreign language | August and December annually, the Deputy Director for SD does monitoring | Elective course program
2 | Preparation of thematic glossaries on subjects studied in the second and third languages ​​according to the content of the curriculum by grade | R-3, CH-1 | Deputy Directors for SD and NMR | Teachers of subjects studied in second and third languages. | 2nd quarter annually Deputy Directors for SD and NMR | Glossaries by subject
3 | Creating conditions for language support for students when studying subjects in a second and third language during class and extracurricular hours. Monitoring the level of language proficiency. | R-3, CH-1 | Methodist | Teachers of Kazakh, Russian and English languages, survey, monitoring results | Annually according to schedule Deputy Director for SD Efficiency is measured by conducting surveys and monitoring student knowledge | Language Support Program for Students with Language Needs
4 | Activation of horizontal planning of teachers in the subjects of the natural science cycle and the humanities cycle with teachers of language disciplines | R-3, CH-1 | Heads of MO Methodist | Methodist, teachers, foreign teachers | Annually according to schedule Deputy Director for SD Monitoring of horizontal planning | Horizontal planning schedule
5 | Effective planning of time for second foreign language lessons | R-3, CH-1 | Deputy Director for SD Methodist | Teachers of a second foreign language | September, January annually Deputy Director for SD | Timetable
6 | Developing procedures to evaluate the effectiveness of services to support students to access education | R-3, CH-1 | Methodist | Methodist, teachers, foreign teachers | Annually according to schedule Deputy Director for SD Monitoring of horizontal planning | Questionnaires, surveys
Priority 3 Organization of career guidance for admission to the Intellectual School, providing support to admitted students |  | Indicator 31 (Indicator 19 from the Strategy) Successful adaptation of newly arrived students 2021 –100% 2022 –100% 2023 –100% 2024 – 100% 2025 – 100% Indicator 32 (Indicator 19 from the Strategy) Number of participants in the Virtual and Vacation School 2021 – functioning 2022 – operational 2023 – operational 2024 – operational 2025 – operational Indicator 33 (Indicator 19 from the Strategy) Number of participants in the Virtual and Vacation School who completed full-time education at school 2021 – operational 2022 – operational 2023 – operational 2024 – operational 2025 – functioning
1 | Carrying out work to attract students to the Virtual School (vacation school) for students in grades 5–6 | R-3, SN-1, P-19 | Teachers responsible for the virtual school Deputy Director for SD | Materials | Annually according to schedule Deputy Director for SD Supervises work to attract students | Promotional materials: brochures and videos Social media posts
2 | Organization of courses at school for students who have passed the Virtual and Vacation School selection | R-3, SN-1, P-19 | Teachers responsible for the virtual school Deputy Director for SD | Materials | Annually according to schedule Deputy Director for SD Supervises work to attract students | Course program and materials
3 | Organization of language courses for newly admitted 7th grade students based on the results of entrance exams | R-3, SN-1, P-19 | Teachers of language subjects, Deputy Director for SD | Materials | Annually according to schedule Deputy Director for SD | Course program and materials
Priority 4 Organization of the Summer School and social practices, expedition “Tugan elge tagzym” for the development of intellectual, research and communication skills of students |  | Indicator 34 (Indicator 12 from the Strategy) Percentage of students, grades 1-12 of Intellectual schools, involved in social projects, practices, actions and additional education 2021 - 90% 2022 - 90% 2023 - 90% 2024 - 90% 2025 year - 90% Indicator 35 (Indicator 13 from the Strategy) Number of products/services prepared by students as part of the “Tugan Elge Tagzym” expedition 2021 – 1 2022 – 2 2023 – 3 2024 – 4 2025 – 5
1 | Development of social practice programs, the “Tugan elge tagzym” expedition, which includes activities for the comprehensive development of the individual (development of skills in serving society, research, art and technological skills) | R-3, CH-1 | Deputy Directors | Teachers, curators | April-May annually | Program and route "Tugan elge tagzym", work plans for research work within the framework of the project "Tugan elge tagzym"
2 | Development of a program of free and paid courses during the Summer School and its promotion among students of secondary schools in the city and region | R-3, CH-1 | Deputy Directors | Teachers, curators | April-May annually | Summer school program, courses offered, applications
Section 7 |  | School culture and partnership
Priority 1 Development of partnerships with various enterprises in the region and city. Participation in international PISA studies. |  | Indicator 36 (Indicator 12 from the Strategy) Number of systemic leadership projects and club works to serve society 2021 - 4 2022 - 5 2023 - 5 2024 - 6 2025 - 6 Indicator 37 Number of implemented projects together with city enterprises 2021 - 4 2022 - 5 2023 - 5 2024 - 5 2025 - 5 Indicator 38 (Indicator 52 from the Strategy) Participation in international studies PISA 2021 - functioning 2022 - functioning 2023 - functioning 2024 - functioning 2025 - functioning
1 | Participation in international PISA studies | R-OS, SN-1, P-52 | Deputy Directors | Analytical reports of the Center for Pilot Studies, Deputy Directors, heads of the Moscow Region, teachers, students of grades 9 and 10. | Analysis of PISA results | Developing teacher reflective skills to improve professional performance using tools for analyzing student learning outcomes.
2 | Development of partnerships with industrial and innovative enterprises of the city and region | R-3, CH-1 | Deputy Directors | memoranda of cooperation, meetings with representatives of industrial organizations | Every year, according to the schedule, the Deputy Director for Development supervises the work | Project programs, Reports on joint events
3 | Organizing the work of the Model UN club and holding meetings at various levels | R-3, CH-1 | Deputy Director for Educational Work | Teachers responsible for running the Model UN club | approval of the work plan in September of each academic year | regional and city conference among students of secondary schools and colleges
4 | Cooperation and organization of joint projects for the development of intellectual and creative skills of students at the city level with the Youth Resource Center and Exhibition Center "Korme" of the city of Shymkent | R-3, CH-1 | Deputy Directors for Educational Work | curators, educators, teachers | Every year, according to the schedule, deputy directors supervise the work in accordance with the joint work plan, the joint work plan is approved in September of each academic year | Project programs, project reports
5 | Organization of educational and educational projects together with city libraries | R-3, CH-1 | Deputy Directors for Educational Work | curators, educators, librarian | Every year, according to the schedule, deputy directors supervise the work in accordance with the joint work plan, the joint work plan is approved in September of each academic year
Priority 2 Further development of the “Partner Schools” project |  | Indicator 6 Number of partner schools in the country and abroad 2021 - 5 2022 - 5 2023 - 5 2024 - 5 2025 - 5 Indicator 39 (Indicator 50 from the Strategy) Number of partners - international organizations 2021 - 3 2022 - 3 2023 - 3 2024 - 3 2025 - 3
1 | Increasing the number of educational organizations in the country and abroad collaborating within the framework of the “Partner Schools” project | R-3, CH-1, I-6 | deputy directors, coordinator of the "Partner Schools" project, teachers | Heads of Moscow Region, teachers | Every year, according to the schedule, the director supervises the work in accordance with the concluded memorandums | Memorandums, Correspondence, Joint projects
2 | Organization of events and mutual visits with partner schools | R-3, CH-1, I-6 | deputy directors, coordinator of the "Partner Schools" project, teachers | Heads of Moscow Region, teachers | Every year, according to the schedule, the director supervises the work in accordance with the concluded memorandums | Mutual visits
Section 8 |  | Material and technical equipment
Priority 1 Creating a more comfortable and modern educational environment at school. |  | Indicator 40 Formation of environmental literacy 2021: cultivation of at least 5 varieties of products that can be used for scientific and research activities of students and implementation within the framework of the Green Lab project. 2022: cultivation of at least 5 varieties of products that can be used for scientific and research activities of students and implemented within the framework of the Green Lab project. 2023: Growing at least 6 varieties of products that can be used for scientific and research activities of students and implemented as part of the Green Lab project. 2024: Growing at least 6 varieties of products that can be used for scientific and research activities of students and implemented as part of the Green Lab project. 2025: Growing at least 6 varieties of products that can be used for scientific and research activities of students and sold within the framework of the Green Lab project. Indicator 41 Promotion of “green technologies” 2021-2023: installation of “smart lights” with motion and time sensors in school bathrooms. The implementation of the project at this stage will save energy resources and contribute to the preservation of the environment. 2024-2025: installation of “smart lights” with motion and time sensors in school corridors. The implementation of the project will significantly save energy resources spent on school lighting. Indicator 42 (Indicator-44 from the Strategy, action 49) Updated material and technical base 2021-2025: modernization of the branch (overhaul) 2021-2025: partial renewal of the school’s material and technical base Indicator 43 Carrying out high-quality ongoing repair work of the school Indicator 44 Number of paid products/services provided by AOO in the country and abroad
1 | Activities to increase the number and diversity of flora on the territory and inside the school. School greenhouse. | R-3, CH-1 | Director, Deputy Director for FHD | Deputy directors, Board of Trustees, Parent Committee, teachers of biology, physics and chemistry, students, parents, technical staff. Staff | Annually and based on need | The school becomes more environmentally responsible and develops eco-friendliness in students and staff. Availability of green areas and school premises with a wide range of flowers, trees and shrubs.
2 | Set of events “NIS in Safety 2025” | R-3, CH-1 | Industrial Safety and Health Engineer, Deputy Director for FHD, Deputy Director for Aircraft | Instructions, information posters, presentations and trainings, intellectual games, creation of a series of animated videos. | Surveys of employees and students every six months. Testing practical knowledge through training exercises according to a separate approved plan. | A number of activities were carried out to improve the safe environment of the school, awareness and coherence of actions in emergency situations among students and staff were increased. Effective procedures are in place to ensure the safety of students and school staff.
3 | Implementation of the project to promote green technologies “Smart light” | R-3, CH-1 | Deputy Director for FCD, Energy | Electricians. Sensors, services for their installation and operation. | The implementation project is designed for 2 years. | The school becomes more environmentally responsible and develops eco-friendliness in students and staff.
4 | Formation of needs for inclusion in the budget for updating and strengthening the material and technical base | R-3, CH-1 | Deputy Director for FCD | Private Enterprise “NIS Service” Private Enterprise CIT | Formation of short-term and long-term budgets | Approved budget and procurement plan
5 | Developing a plan and conducting regular fire safety and other emergency drills (lockdown) | R-3, CH-1 | Health and Safety Inspector | IT specialists, teachers responsible for blocks during evacuation | Annually according to schedule Deputy Director for HR Supervises the work | Exercise plan
6 | Providing logistical support in organizing school security | R-3, CH-1 | Educational and support staff of the school | School staff | Annually according to schedule | Action plan for improvement of the school grounds and development of the internal infrastructure of the school
7 | Effective planning of the current annual and medium-term budgets, as well as the capital expenditure budget for strengthening the MTB school, based on the regulatory documents of Nazarbayev Intellectual Schools JSC and the forecast of annual macroeconomic indicators | R-OS, SN-1, P-44 | Deputy Director | Economist-planner, economist-treasurer | According to the order of the AOO, within the established time limits, annually | Creating favorable conditions for school activities to provide goods, works, and services.
11 | Carrying out high-quality cosmetic repairs to the school | R-OS, CH-1, P-42 | Deputy Director | Household manager, power engineer, | annually | Maintaining the school building and premises in proper condition for the learning process of students.
12 | Taking measures to improve the school grounds and develop the internal infrastructure of the school | R-3, CH-1 | Educational and support staff of the school | School staff | Annually according to schedule | Action plan for improvement of the school grounds and development of the internal infrastructure of the school
13 | Analysis and control of accounting, timely submission of financial, tax and statistical reporting. | R-OS, SN-1, P-44 | Chief Accountant | Legal acts of JSC NIS, RK, as well as assumed obligations with counterparties. | Performers: accounting staff - during the financial year | Financial stability, timely control and accounting.
14 | Provision of paid services - paid educational services and sale of teaching materials, agricultural books. products. | R-OS, SN-1, P-44 | Deputy Directors, Ch. accountant | Educational process, educational programs, teaching materials - books on the COP project, greenhouse products - cucumbers. | Performers-teachers, school staff. During a year. | Income from paid services.
Section 9 |  | Other school activities
1 | Conducting explanatory work on regulatory documents for the school community and ensuring their further application in practice | R-3, CH-1 | Lawyer HSE Engineer | Heads of educational institutions, teacher-organizers-curators, teachers, technical staff | August-September annually Deputy Directors Attendance at events to clarify regulatory documents | Knowledge of regulations and compliance with them Orientation days program
2 | Developing a plan and conducting regular fire safety and other emergency drills (lockdown) | R-3, CH-1 | HSE engineer | Heads of educational institutions, teacher-organizers-curators, teachers, students, technical staff | Annually according to schedule Supervising Deputy Director | Schedule of practical exercises
3 | In order to successfully complete the process of confirming the status of an accredited school, work will continue to organize safe conditions and life activities. | R-3, CH-1 | Deputy Directors HSE Engineer | Heads of educational institutions, teacher-organizers-curators, teachers, students, technical staff | Constantly | Ensuring the health and life safety of those in the school building
4 | Conducting a class on anti-terrorism training with teaching staff, administrative staff and technical personnel, as well as conducting activities to practice joint actions with interested government bodies and organizations to eliminate man-made threats that arose as a result of an act of terrorism. | R-3, CH-1 | Health and safety engineer Employees of the Shymkent Police Department | Heads of educational institutions, teacher-organizers-curators, teachers, students, technical staff | According to the work plan | Knowledge of all staff and students in the event of a possible threat of a terrorist attack and what to do when suspicious objects are found in the school building
5 | In order to comply with the requirements of administrative and criminal procedural offenses of the Republic of Kazakhstan, as well as to prevent various incidents among teenagers with students in grades 11-12, conduct explanatory work and a seminar with the invitation of employees of the prosecutor's office and juvenile police of the local police service. | R-3, CH-1 | Health and safety engineer Employees of the Shymkent Police Department | Heads of educational institutions, teacher-organizers-curators, teachers, students, technical staff | According to the work plan | Knowledge of regulations and compliance with the laws of the Republic of Kazakhstan
6 | Organize and conduct, with the invitation of employees of the Emergency Management Department of the Karatau region, a seminar on the topic “Fire safety in everyday life, as well as in crowded places” and “Action of people in the event of a fire.” | R-3, CH-1 | HSE engineer Employees of the Karatau emergency department in Shymkent | Heads of educational institutions, teacher-organizers-curators, teachers, students, technical staff | According to the work plan | Compliance with fire safety measures in buildings and at home
7 | Providing timely first aid | R-3, CH-1 | Medical workers | Heads of the Ministry of Defense, medical workers, teacher-organizers-curators, teachers, students, boarding school teachers, technical staff | Daily | Providing timely first aid
8 | Always have a supply of medical supplies and instruments for medical care | R-3, CH-1 | Medical workers, economists, pharmacy employees | Medical workers, economists, pharmacy employees | According to applications and plan | Always have a supply of medical supplies and instruments
9 | Activities to promote a healthy lifestyle | R-3, CH-1 | Medical workers, specialists from healthy lifestyle centers and medical institutions | Medical workers, specialists from the healthy lifestyle center and medical institutions, teacher-organizers-curators, educators, safety and security engineer | According to the work plan | Lectures, conversations, round tables and meetings
10 | Carrying out preventive work to prevent infectious diseases, preventive vaccinations, sanitary and epidemic measures | R-3, CH-1 | Medical workers, SES specialists and other medical institutions | Medical workers, SES specialists and other medical institutions, teacher-organizers-curators, educators, | According to the work plan | Lectures, conversations, vaccinations.
11 | Organize a dombra orchestra and a dance group from among the students of the hostel | R-3, CH-1 | Educators, additional education teachers | Educators, additional education teachers | 2021-2022 academic year | Participation in creative competitions on a city, regional and national scale, performance in school events
12 | Formation of independent library user skills in students: learning to use books and other media, search, select and critically evaluate information | R-3, CH-1 | Teacher-librarians | Teacher-librarians, library lessons | According to the work plan | development of information and functional literacy skills, critical thinking skills
13 | Information support for teachers and students in educational and research activities | R-3, CH-1 | Teacher-librarians | Teacher-librarians, webinar and training on using resources | According to the work plan | Active use of library and educational resources